## Overview
Test Plan KSP |  |  | @dropdown
Overview
Reference Information | Location | Comments
Use Cases & Requirements | [Link]
Reference Material | [Link]
Test Environment information | [Link]
End User Documentation | [Link]
Test Schedule | [Link]
Change Log | Person | Date |  | Test Instructions
Created Doc | Tatyana Zima | 3-mar.-24
| Ibrahem Shahbary | 3-mar.-24
| Oleg Nykhaychuk | 3-mar.-24
| Daget Tasama | 3-mar.-24
| Hadas | 3-mar.-24 3-apr-24
Test Results Summary (Auto Calculated) | Number | Percent |  | Run Instructions
Total Test Cases Passed | 226 | 93.78% |  | In the "Status" column, use Pass, Fail, Not Applicable,Not Relevant or Not Started.
Total Test Cases Failed | 15 | 6.224% |  | Totals and color highlighting will update automatically based on the Status column
Total Test Cases N/A and N/R | 0 | 0%
Total Test Cases Remaining | 0 | 0%

## LoginIBRAHIM
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario | Login / Register | Total Passed | 21 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 2 |  |  |  | Fail
Prerequisite | Open Website Successfully | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
| Connecting to the system through an account | [5 empty] | Blocked
The site is open on the log in
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
LOG-1-1 | Click on the account button, click on the profile button | after click profile open התחברות |  | Pass
LOG-1-2 | after im open folder log in i click register | Open by logging in to create an account |  | Pass
LOG-1-3 | Create a New Account. I click register an open a new account | Test Create Account | LAST NAME : Ahmad First NAME: shahbary email: ibrahem.sh152@gmail.com Number: 0506866888 Password:@Asd123456a | Pass
LOG-1-4 | after finishing registering I checked my phone You did not receive a message | Messaga Not Receive |  | Fail |  | No send SMS To Phone
LOG-1-5 | after register I check my email and I get a Verify Email Address for KSP | Send To email Verify successfully |  | Pass
LOG-1-6 | test last name disable register | i check last name disable | last name:hh | Pass
LOG-1-7 | test first name disable register | i check first name disable | first name: gg | Pass
LOG-1-8 | test email disable register | i check email disable | email: asda@hkam | Pass
LOG-1-9 | test numper disable register | i check numper disable | numper: 812317@#! | Pass
LOG-1-10 | test password disable register | i check paswword disable | password :!@#$%^&*(() | Pass
LOG-1-11 | I'm open website KSP and after this, I click on the account button, and the profile button, to make a login | Test Log In | email : ibrahem.sh152@gmail.com password : @Asd123456a | Pass
LOG-1-12 | After opening the account successfully. I went and clicked to log out of the account succesfully | after log in i want test log out |  | Pass
LOG-1-13 | after i click forget password open page Reset password | click on forget password |  | Pass
LOG-1-14 | Write my email and click restart password, I get an email link website to restart password | restart password | Reset password : ibrahem.sh152@gmail.com | Pass
LOG-1-15 | After clicking on the link website successfully , restart the password | click on the email link website to restart password |  | Pass
| i open log in to test new password succesfully | new password | password: !@Asd123as agine password : !@Asd123as | Pass
LOG-1-16 | not send a message to me this is disabled on log-in to tell to my email + password not successfully | Test Disable email + paswword Log in | email : fash@gmash.com password : !@#$hfasg23 | Fail |  | no get email or password error
LOG-1-17 | After Log In, i click on the Delete Account | The operation was successfully performed after the confirmation you will be disconnected from the use | email: asd@hma.com | Pass
LOG-1-18 | after im log in open folder personal arean | personal data successfully | personal data | Pass
LOG-1-19 | after open page personal area i click My Orders | My Orders successfully | My Orders | Pass
LOG-1-20 | after open My Orders, i Click Items Liked | Items Liked successfully | Items Liked | Pass
LOG-1-21 | after Open Items Liked, i click history of clients | history of clients successfully | History of clients | Pass
LOG-1-22 | after open history of clients, i click debit permissions | debit premissions successfully | debit premissions | Pass
LOG-1-23
LOG-1-24
LOG-1-25
LOG-1-26
LOG-1-27
LOG-1-28
LOG-1-29
LOG-1-30
LOG-1-31
LOG-1-32
LOG-1-33
LOG-1-34
LOG-1-35
LOG-1-36
LOG-1-37
LOG-1-38
LOG-1-39
LOG-1-40
LOG-1-41
LOG-1-42
LOG-1-43
LOG-1-44
LOG-1-45
When you type an incorrect email or password, it does not show that there is an error and opens blank pages

## BranchesIBRAHIM
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario | Login / Register | Total Passed | 18 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 1 |  |  |  | Fail
Prerequisite | Open Website Successfully | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
| Connecting to the system through an account | [5 empty] | Blocked
The site is open on the branche & hours button
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
BRAN-1-01 | click on the services button , click on the branche & hours button | after I click branche and Hours I go to Branches and Opening hours |  | Pass
BRAN-1-02 | After page open i click Search branch English | Search not work English | 1. afula 2. ashdod 3. ashdod city 4. ashkelon 5. bat yam 6. beer sheva ramot 7.berr shava east 8. beit shemesh 9. bilu 10. bnei brak 11. eilat ha'laguna 12. eilat taielet 13. eilat tarshish 14. eilat tourism center 15. hadera 16. haifa matam 17. haifa romema 18. haifa stella maris 19. herzliya center 20. herzliya pituah 21. hod hasharon 22. holo 23. jer king george 24. jerusalem har hotzvim 25. jerusalem talpiot 26. karmiel 27. kfar saba green 28. kfar-sabe 29. kiryat gat 30. kiryat-atta 31. kiryat-bialik kiryon 32. kiryat- haim 33.kiryat-ono 34. modiin 35. nahariya 36. nesher 37. ness ziona 38. netanya a-sharon mall 39. netanya kiryat-sharon 40.netanya poleg 41. netivot 42. nof hagalil (nazareth-illit) 43.petah-tikva rabin 44.petah-tikva sgula 45.ra'anana 46.ramat gan 47. ramat hasharon 48. ramle 49.rehovot 50.rishon lezion canter 51. rishon lezion rozhansk 52.rosh haayin 53.tel aviv - tagor ramat aviv 54.tel aviv hahashmonaim 55. tel baruch 56. tel aviv dizingof 57. tel aviv ha'masger 58. tel aviv ramat ahayal 59.tiberias 60. yavne | Fail
BRAN-1-03 | After page open i click Search branch Hebrew | Search work Hebrew | 1. עפולה 2. אשדוד 3. העיר אשדוד 4. אשקלון 5. בת ים 6. באר שבע רמות 7.בר שאווה מזרח 8. בית שמש 9. בילו 10. בני ברק 11. אילת הלגונה 12. אילת טיילת 13. אילת תרשיש 14. מרכז תיירות אילת 15. חדרה 16. חיפה מתאם 17. חיפה רומה 18. חיפה סטלה מאריס 19. מרכז הרצליה 20. הרצליה פיתוח 21. הוד השרון 22. הולו 23. ג'ר קינג ג'ורג' 24. ירושלים הר חוצבים 25. תלפיות ירושלים 26. כרמיאל 27. ירוק כפר סבא 28. כפר סבה 29. קרית גת 30. קרית-עטה 31. קרית-ביאליק קריון 32. קרית חיים 33.קרית-אונו 34. מודיעין 35. נהריה 36. נשר 37. נס ציונה 38. קניון נתניה א-שרון 39. נתניה קרית-שרון 40.נתניה פולג 41. נתיבות 42. נוף הגליל (נצרת עילית) 43.פתח-תקווה רבין 44.פתח-תקווה סגולה 45.רעננה 46.רמת גן 47. רמת השרון 48. רמלה 49.רחובות 50.ראשון לציון קנטר 51. ראשון לציון רוז'נסק 52.ראש העין 53.tel aviv - תגור רמת אביב 54.תל אביב החשמונאים 55. טל ברוך 56. תל אביב דיזינגוף 57. תל אביב המסגר 58. תל אביב רמת החייל 59.טבריה 60. יבנה | Pass
BRAN-1-04 | click on the עפולה | open page Hours and Branche successfully | עפולה | Pass
BRAN-1-05 | click on the אשדוד | open page Hours and Branche successfully | אשדוד | Pass
BRAN-1-06 | click on the העיר אשדוד | open page Hours and Branche successfully | העיר אשדוד | Pass
BRAN-1-07 | click on the אשקלון | open page Hours and Branche successfully | אשקלון | Pass
BRAN-1-08 | click on the בת ים | open page Hours and Branche successfully | בת ים | Pass
BRAN-1-09 | click on the אילת הטיילת | open page Hours and Branche successfully | אילת הטיילת | Pass
BRAN-1-10 | click on the אילת לגונה | open page Hours and Branche successfully | אילת לגונה | Pass
BRAN-1-11 | click on the אילת מרכז התיירות | open page Hours and Branche successfully | אילת מרכז התיירות | Pass
BRAN-1-12 | click on the אילת תרשיש | open page Hours and Branche successfully | אילת תרשיש | Pass
BRAN-1-13 | click on the 'אילת הטיילת' button , click on the 'קביעת תור לסניף' button | open page 'קביעת תור לסניף' successfully | אילת הטיילת | Pass
BRAN-1-14 | click on the 'אשקלון' button, click on the 'קביעת תור לסניף' button | open page 'קביעת תור לסניף' successfully | אשקלון | Pass
BRAN-1-15 | click on the 'קרית אונו' button, click on the 'קביעת תור לסניף' button | open page 'קביעת תור לסניף' successfully | קרית אונו | Pass
BRAN-1-16 | after open קביעת תור לסניף Put number Disable | numper Disable יש להזין מספר טלפון נייד תקין בן 10 ספרות בלבד | 5045998781 | Pass
BRAN-1-17 | after open קביעת תור לסניף Put number מוקדים טלפונים disable | numper Disable יש להזין מספר טלפון נייד תקין בן 10 ספרות בלבד | 03-5086905 | Pass
BRAN-1-18 | after open קביעת תור לסניף Put my number succesfully | numper succesfully הודעה עם פרטי התור תגיע למספר שהוזן בדקות הקרובות | 050-6866888 | Pass
BRAN-1-19 | after send to my numper message i click in link open הזמנת תור לסניפי ksp | open הזמנת תור לסניפי KSP |  | Pass
BRAN-1-20
BRAN-1-21
BRAN-1-22
BRAN-1-23
BRAN-1-24
BRAN-1-25
BRAN-1-26
BRAN-1-27
BRAN-1-28
BRAN-1-29
BRAN-1-30
BRAN-1-31
BRAN-1-32
BRAN-1-33
BRAN-1-34
BRAN-1-35
BRAN-1-36
BRAN-1-37
BRAN-1-38
BRAN-1-39
BRAN-1-40
BRAN-1-41
BRAN-1-42
When you type an incorrect email or password, it does not show that there is an error and opens blank pages

## Compare productsIBRAHIM
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario | Login / Register | Total Passed | 9 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 0 |  |  |  | Fail
Prerequisite | Open Website Successfully | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
| Connecting to the system through an account | [5 empty] | Blocked
The site is open on the products comparison
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
COMP-1-01 | click on the TV category button, click on the TV category Button, Click on any television prodact, click on the '' products compariosn '' Button ' add to the comparison list ' , click on the acconunt button , click on the products compariosn button | this product appears add to the comparison list | Samsung 50 Inch Crystal UHD 4K HDR Smart TV UE50CU7100 | Pass
COMP-1-02 | click on the sports button, click on the basketball button, click on any baden sprots elite microfiber basketball size 7, click on the '' produts compariosn '' button ' add to the copmarison list ' , click on the account button , click on the products compariosn button | this product appears add to the comparison list | Baden Sports Elite Microfiber Basketball Size 7 | Pass
COMP-1-03 | click on the for pets button, click on the for cat button, click on any Litter-Robot 4 Open Air Automatic Self-Cleaning Cat Litter Box Black , click on the '' produts copmariosn '' button ' add to the copmarison list ', click on the acount button .click on the products copmariosn button | this product appears add to the comparison list | Litter-Robot 4 Open Air Automatic Self-Cleaning Cat Litter Box Black | Pass
COMP-1-04 | click on the account button, click on the products comparison button, click on the Delete button | the delete work successfully | Delete | Pass
COMP-1-05 | click on the garden button, click on the garden office button, click on the Palram Copenhagen Garden Office 3.5X2.9 , click on the produts copmarison buttone ' add to the copmarison list ', click on the back page button, click on the pools&accesson button, click on the Bestway Power Steel Pool 412X201X122, click on the produts '' copmarison buttone '' button ' add to the copmarison list ', click on the account button, click on the produts promaison button | add 2 products comparison successfully | 1.Palram Copenhagen Garden Office 3.5X2.9 2. Bestway Power Steel Pool 412X201X122 | Pass
COMP-1-06 | click on the babies button, click on the high chairs button click on any Sitting chair, click on the ''produts copmarison'' buttone ' add to the copmarison list ', click back page home button, click on the audio button, click on the headphones button, click on any headphones, click on the ''products compariosn'' Button ' add to the comparison list ', click back home page button, click on the perfumes button, click on the gift set for men button, click on any gitf , click on the 'products compariosn' Button ' add to the comparison list ' , click on the account button, click on the produts promaison button | add 3 products comparison successfully | 1. Baby Boss Pluma Baby High Chair Camel 2.Apple AirPods Pro (2nd generation) - With MagSafe Charging Case (USB‑C) 3.Versace Pour Homme Dylan Blue Mens Gift Set 100mlEau De Toilette E.D.T + Shower Gel | Pass
COMP-1-07 | click on the account button, click on the products comparison button, click on the go to products comparison page | open page Product comparison |  | Pass
COMP-1-08 | after open Product comparison, click on the ' mak differences between products ' button | 1.If there is no difference, it is white 2.When there is a difference between two devices, they are marked as yellow | 1. Samsung 75 Inch Crystal UHD 4K HDR Smart TV UE75CU7100 2. Samsung 50 Inch Crystal UHD 4K HDR Smart TV UE50CU7100 | Pass
COMP-1-09 | I want to add 4 items or more In products promaison | A red file appears written in it 1.You can compare up to 3 products 2.Cancel selected products |  | Pass
COMP-1-10
COMP-1-11
COMP-1-12
COMP-1-13
COMP-1-14
COMP-1-15
COMP-1-16
COMP-1-17
COMP-1-18
COMP-1-19
COMP-1-20
COMP-1-21
COMP-1-22
COMP-1-23
COMP-1-24
COMP-1-25
COMP-1-26
COMP-1-27
COMP-1-28
COMP-1-29
COMP-1-30
COMP-1-31
COMP-1-32
COMP-1-33
COMP-1-34
COMP-1-35
COMP-1-36
COMP-1-37
COMP-1-38
COMP-1-39
COMP-1-40
When you type an incorrect email or password, it does not show that there is an error and opens blank pages

## ProductOleg
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario |  | Total Passed | 57 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 1 |  |  |  | Fail
precondition | the site working and the product section is open and any product page open | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
Blocked
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
ACCE-2-1 | press the button"מסכי טלוויזיה ואביזרים" | the screen opened''טלוויזיות" |  | Pass
ACCE-2-2 | select one from all provided | the screen with the selected |  | Pass
ACCE-2-3 | select SAMSUNG 50" crystal UHD 4k HDR UE50CU7100 טלוויזיה חכמה מק״ט KSP 261840 | display SAMSUNG 50" crystal UHD 4k HDR UE50CU7100 טלוויזיה חכמה מק״ט KSP 261840 |  | Pass
ACCE-2-4 | verify visually uf all page elements are displayed | all elements of page are displayed |  | Pass
ACCE-2-5 | check if follwing us diplayed"משלוח חינם לבית הלקוח" | display |  | Pass
ACCE-2-6 | click on the inscription "עד 7 תשלומים ללא ריבית" | the screen opened"מחשבון תשלומים" |  | Pass
ACCE-2-7 | select"תשלומים7" | result "7 תשלומים ללא ריבית" |  | Pass
ACCE-2-8 | select "8 תשלומים" | result addition ריבית "8 תשלומים " |  | Pass
ACCE-2-9 | click on the"סגירה",return to original page | return to original page |  | Pass
ACCE-2-10 | click on the "x" ,return to original page | return to original page |  | Pass
ACCE-2-11 | check if follwing us diplayed "משלוח ישיר לבית הלקוח בלבד" | display |  | Pass
ACCE-2-12 | click on the"הטבה לרוכשים" | the screen opens"הטבות" |  | Pass
ACCE-2-13 | click "הוספה לעגלה" | the screen opens "המוצר התווסף בהצלחה לעגלת הקניות" |  | Pass
ACCE-2-14 | click "מעמד שלתים אלגנטי" | the screen opens"מעמד שלתים אלגנטים" |  | Pass
ACCE-2-15 | click" "הוספה לעגלה"" | the screen opens "המוצר התווסף בהצלחה לעגלת הקניות" |  | Pass
ACCE-2-16 | press to return the page | return to original page |  | Pass
ACCE-2-17 | click on the "התקנה ומיתקן תליה ב-99 שקל" | a pop-up with conditions "התקנה ומיתקן תליה ב-99 שקל" |  | Pass
ACCE-2-18 | click on the "לתקנון מלה>>" | the page opens "תנאי רכישה מסכי סמסונג" |  | Pass
ACCE-2-19 | press to return the pages | return to original page |  | Pass
ACCE-2-20 | click on the " שקל הנחה 50״ | a page opens explaining howto use"שקל הנחה50 " |  | Pass
ACCE-2-21 | press"סגירה" to return the pages | return to original page |  | Pass
ACCE-2-22 | click "ננצח כל הצעת מחיר שתימצו" | to screen opens"מצתם זול יתר?" |  | Pass
ACCE-2-23 | fill in the form.validation is present in the form | there's a button"שליחת טופס" |  | Pass
ACCE-2-24 | click button "שליחת טופס" | pop-up appeared, that the application is accepted and returns to the original page |  | Pass
ACCE-2-25 | click on the "עדכנו אותי על ירידת מחיר" | to screen opens "עדכנו אותי על ירידת מחיר" |  | Pass
ACCE-2-26 | fill out request form indicating ימים 5 בחירת ימים להתראה" and press to the button "שליחת טופס"״ | pop-up appeared, that the application is accepted and returns to the original page |  | Pass
ACCE-2-27 | hover mouse over the question mark next to"שלמו בהוראת קבע/תשלומים ללא תפיסת מסגרת" | pop-up appears "אופציות למספר תשלומים" |  | Pass
ACCE-2-28 | in paragraphe"בחירת אינץ"select 55" | the price of the product has changed.unch size hasbecome blue.the price under the inch iconis not show |  | Pass
ACCE-2-29 | click to the button"כמות" +"or"-" to change the order quantity | the number of order units is changed by pressing"+" or"-"next to the button"כמות" |  | Pass
ACCE-2-30 | click to the button"הוספה לעגלה" | the screen opens "המוצר התווסף בהצלחה לעגלת הקניות" |  | Pass
ACCE-2-31 | press the button"מחשבים וסלולר" | the screen opened''מחשבים וסלולר" |  | Pass
ACCE-2-32 | press the button"טלפונים סלולרים" | a screen opened with a selection of models and manufactures |  | Pass
ACCE-2-33 | press to select mobile "Apple iphone 15 pro max 256 GB"מק״ט 268701 | the screen with the specified model |  | Pass
ACCE-2-34 | check visually if all elements are displayed | all elements of page are displayed |  | Pass
ACCE-2-35 | check if it is displayed "משלוח חינם לבית הלקוח" | displayed on the page |  | Pass
ACCE-2-36 | check if it is displayed"מישלוח לנקודת איסוף חינם" | displayed on the page |  | Pass
ACCE-2-37 | check if it is displayed"עד 24 תשלומים ללא ריבית" | displayed on the page |  | Pass
ACCE-2-38 | press the button "עד 24 תשלומים ללא ריבית" | opened page"מחשבון תשלומים" |  | Pass
ACCE-2-39 | check all product data ,including the possbility of"עד 24 תשלומים ללא ריבית" | product data is correct,possibility "עד 24 תשלומים ללא ריבית" the options is available |  | Pass
ACCE-2-40 | n the frameו "בחרו מספר תשלומים",select ״25 תשלומים" | in choosing more "עד 24 תשלומים ללא ריבית" payment amount with interest |  | Pass
ACCE-2-41 | click on "סגירה" or "X" return to the original screen | return to the original screen |  | Pass
ACCE-2-42 | click on "לבדיקה מלאי בסניפים לחץ כן" | a page opens with "בדיקה זמינות מלאי בסניפי " |  | Pass
ACCE-2-43 | click on "סגירה" or "X" return to the original screen | return to the original screen |  | Pass
ACCE-2-44 | go to " בחירת נפח אחסון" and select 512 GB | the price of the product has changed.unch size hasbecome blue.the price under the inch iconis not show |  | Pass
ACCE-2-45 | click on "בחירת צבע" select" טיטניום כחול" | color selected " טיטניום כחול" |  | Pass
ACCE-2-46 | click on pop-up "בצעו טרייד-אין ו חסכו עד 3,199 שקל" | a page opened "בצעו טרייד-אין ו חסכו עד 3,199 שקל" |  | Pass
ACCE-2-47 | click on "סגירה" or "X" return to the original | return to the original screen |  | Pass
ACCE-2-48 | in the "תיאור קצר " click on "לסקירה המלאה>" | the page goes down and displays"סקירה" |  | Pass
ACCE-2-49 | click on the "הטבות והצעות משלימות ברכישת מוצר זה" | displays different lucrativeoffers when you purchase thus product |  | Pass
ACCE-2-50 | click on "הוספה לעגלה" | the following page is displayed "המוצר התווסף בהצלחה לעגלת הקניות" |  | Pass
ACCE-2-51 | click on the"להמשך קנייה" | return to the original page before continuing shopping |  | Pass
ACCE-2-52 | click on the "כמות" with the button "+"to increase the number of purchases up to 6 pieses | a notification comes up that the maximum number of purchases of this product is 5 pcs |  | Fail
ACCE-2-53 | click on the icon"F" | go to the KSP Facebook page |  | Pass
ACCE-2-54 | click on the icon"קישור לעמוד יצרן" | go to the page |  | Pass
ACCE-2-55 | click on the icon"הדפסת מוצר" | sending the product to the prunter for printing |  | Pass
ACCE-2-56 | click on the icon"העתקת קישור ללוח" | a message is displayed "הקישור הועתק בהצלחה" |  | Pass
ACCE-2-57 | when the button is press" הוספה להשוואה דגמים"it si displayed in blue"הסרה מהשוואת דגמים" | press " הוספה להשוואה דגמים" it si displayed in blue ״הסרה מהשוואת דגמים" |  | Pass
ACCE-2-58 | when the button is "הוספה לפטים שאהבתי" it is displayed in red"הסרה מרטים שאהבתי" | press " הוספה לפטים שאהבתי" it is displayed in red "הסרה מרטים שאהבתי" |  | Pass
ACCE-2-59
ACCE-2-60
ACCE-2-61
ACCE-2-62
ACCE-2-63
ACCE-2-64
ACCE-2-65
ACCE-2-66
ACCE-2-67
ACCE-2-68
ACCE-2-69

## SaleOleg
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario |  | Total Passed | 11 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 1 |  |  |  | Fail
precondition | the site working and the product section is open and any product page open | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
Blocked
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
SALE-2-01 | click on "לפרטים נוספים"on the screen ASUS | Ascreen with the product and the discounted price was opened |  | Pass
SALE-2-02 | check if the discount is displayed 3,684 shekel instead 5,499 shekel | the discount is displayed on the screen |  | Pass
SALE-2-03 | click on the "מבצעי מרץ-מחשב נייד ב 33%הנחה(מוגבל אחד ללקוח)" | the page with the possibility to buy the product at a discount has opened |  | Pass
SALE-2-04 | click on the "הוספה לעגלה" | a message is displayed " המוצר נוסף בהצלחה" |  | Pass
SALE-2-05 | choose two products and see if there is a discount | you can buy two products at a discount |  | Fail
SALE-2-06 | click on the screen"קופון הטלגרם"on the line "לפרטים נוספים" | opened a link to a telegram site with"קופון הקיץ" |  | Pass
SALE-2-07 | sing up for telegram to get the discount | registration onthe site telegram |  | Pass
SALE-2-08 | click on the screen "קונים מעבד מזון *megimix* ו מקבלים סט 3 דיסקיות " and press button "לרכישה" | the product selection screen opens"megimix" |  | Pass
SALE-2-09 | select "megimix 5200 JXL"מק״ט 92022 | a screen popped up with "megimix 5200JXL מק״ט92022" |  | Pass
SALE-2-10 | clik on the " הוספת לעגלה" | a screen popped with " עגלת קניות שלכם" |  | Pass
SALE-2-11 | check if ""קונים מעבד מזון *megimix* ו מקבלים סט 3 דיסקיות" relevant | displays that relevant |  | Pass
SALE-2-12 | buy 5 pieces of this product and check if there is a discount on all 5 pieces | discount applies to all 5 pieces |  | Pass
SALE-2-13
SALE-2-14
SALE-2-15
SALE-2-16
SALE-2-17
SALE-2-18
SALE-2-19
SALE-2-20
SALE-2-21
SALE-2-22
SALE-2-23
SALE-2-24
SALE-2-25
SALE-2-26
SALE-2-27
SALE-2-28
SALE-2-29
SALE-2-30
SALE-2-31
SALE-2-32
SALE-2-33
SALE-2-34
SALE-2-35
SALE-2-36
SALE-2-37
SALE-2-38
SALE-2-39
SALE-2-40
SALE-2-41
SALE-2-42
SALE-2-43
SALE-2-44
SALE-2-45
SALE-2-46
SALE-2-47
SALE-2-48
SALE-2-49
SALE-2-50
SALE-2-51
SALE-2-52
SALE-2-53
SALE-2-54
SALE-2-55
SALE-2-56
SALE-2-57
SALE-2-58
SALE-2-59
SALE-2-60
SALE-2-61
SALE-2-62
SALE-2-63
SALE-2-64
SALE-2-65
SALE-2-66
SALE-2-67
SALE-2-68
SALE-2-69

## AccessibilityOleg
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario |  | Total Passed | 15 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 2 |  |  |  | Fail
precondition | the site working and the product section is open and any product page open | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
Blocked
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
ECCE-2-01 | click on the button "נגישות"located next to logo KSP | the screen in the upper left corner opened"תפרית נגישות" |  | Pass
ECCE-2-02 | click on button"גווני אפור" | the color of the screen became"גוון אפור" |  | Pass
ECCE-2-03 | click on the button " איפוס" | the screen returned to its original colors |  | Pass
ECCE-2-04 | click on the button "ניגודיות הפוכה" | the color of the screen became"black and with yellow lettering" |  | Pass
ECCE-2-05 | click on the button " איפוס" | the screen returned to its original colors |  | Pass
ECCE-2-06 | click on the button"הקטנת טקסט" | the text should shrink in relation to the original text |  | Fail
ECCE-2-07 | click on the button " איפוס | the screen us back to its original appearance |  | Pass
ECCE-2-08 | click on the button"הגדלת טקסט" | the text on thescreen increases each time the button is pressed "הגדלת טקסט" |  | Pass
ECCE-2-09 | click on the button"איפוס" | after pressing the button"הגדלת טקסט" the screen "תפריט נגישות" is partially displayed |  | Fail
ECCE-2-10 | click on the button "הקטנת טקסט" | the text on thescreen has returned to is original size |  | Pass
ECCE-2-11 | click on the button"הגדשת כותרות" | all headingon the site are underlined with a line |  | Pass
ECCE-2-12 | click on the button "איפוס" | the screen us back to its original appearance |  | Pass
ECCE-2-13 | click on the button"הגדשת קישורים" | all links on the site are underlined with a line |  | Pass
ECCE-2-14 | click on the button "איפוס" | the screen us back to its original appearance |  | Pass
ECCE-2-15 | click on the button"עצירת נימציה" | all animations on the site are not movable |  | Pass
ECCE-2-16 | click on the button "איפוס" | the screen us back to its original appearanc |  | Pass
ECCE-2-17 |  | the |  | Pass
ECCE-2-18
ECCE-2-19
ECCE-2-20
ECCE-2-21
ECCE-2-22
ECCE-2-23
ECCE-2-24
ECCE-2-25
ECCE-2-26
ECCE-2-27
ECCE-2-28
ECCE-2-29
ECCE-2-30
ECCE-2-31
ECCE-2-32
ECCE-2-33
ECCE-2-34
ECCE-2-35
ECCE-2-36
ECCE-2-37
ECCE-2-38
ECCE-2-39
ECCE-2-40
ECCE-2-41
ECCE-2-42
ECCE-2-43
ECCE-2-44
ECCE-2-45
ECCE-2-46
ECCE-2-47
ECCE-2-48
ECCE-2-49
ECCE-2-50
ECCE-2-51
ECCE-2-52
ECCE-2-53
ECCE-2-54
ECCE-2-55
ECCE-2-56
ECCE-2-57
ECCE-2-58
ECCE-2-59
ECCE-2-60
ECCE-2-61
ECCE-2-62
ECCE-2-63
ECCE-2-64
ECCE-2-65
ECCE-2-66
ECCE-2-67
ECCE-2-68
ECCE-2-69

## Customer ServiceDavid
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario |  | Total Passed | 6 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 1 |  |  |  | Fail
prerequest | Open Website Successfully | Total N/A, N/R and Blocked | 3 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
Blocked
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link /bug | Comments
SERV-3-1 | 1.enter the site "https://ksp.co.il/web/" 2.In the second line, click on ״שירות לקוחות ״ 3.We will check the operating hours that are shown to us 4.We will check response time | 1.Entered 2.Customer Service page open 3.The operating hours work at the written time 4.The waiting time is longer than usual due to a lack of personnel |  | Pass
SERV-3-2 | 1.Click on the option of addresses and hours of operation 2.We will select one store and perform a response test | 1.We received a list of stores and operating hours in the country 2.We received an answer to the store at the address |  | Pass
SERV-3-3 | 1. Enter the second line ״בירורים לפני ביצוע הרכישה״ 2.Click on the first line "Questions about products and their availability in stock" 3.We will have the option of receiving service via WhatsApp or email 4.We will check your availability on WhatsApp and the email | 1.A list of four information options will open 2.We will receive information about products and stock 3.4. We received WhatsApp service after one business day and email after 3 days |  | Pass
SERV-3-4 | 1. Go to the second line "Order process" 2. We will select a product and check availability 3. We will check delivery times | 1.Enters a monitor that gives information about the ordering process 2. After we have selected a product, we will receive information about its availability and inventory 3. After I have added the product to the cart, we will receive delivery times according to my residence |  | Pass
SERV-3-5 | 1.In the third line Click on ״בדיקת סטטוס הזמנה שביצעתי״ 2.We will enter an order number and a phone number | Unable to check |  | Not Applicable
SERV-3-6 | 1. Enter the third in "בירורים אחרי ביצוע רכישה" 2. clicked on and enters the" שירות ותמיכה טכנית לאחר קנייה " 3.Then enter a phone number and a serial number | unable to check |  | Not Applicable
SERV--3-8 | 1.Enter ״שירות לקוחות״ 2.Click on the third line 3.Click on the fourth line ״שחזור חשבונית״ 4.Write the phone number on the line | 1.Customer service will be opened 2.Open the options 3.The invoice recovery page opens |  | Not Applicable
SERV-3-9 | 1.Enter customer service 2.Click on the third line ״בירורים אחרי ביצוע רכישה״ 3.click on the last " החזרה או החלפה של מוצר תקול" 4.Click on ״ עדיין לא עברו 14 יום ממועד הרכישה״ 5.Click on the last line "נדרש שירות לכל מוצר אחר" 6.and enter a telephone/serial number | 1.The page opens in customer service 2.The requested service opens 3.And we will get the option to fill in a phone/serial number |  | Pass
SERV-3-10 | 1.Go to the customer service page 2.Click on the third line״בירורים אחרי ביצוע רכישה״ 3.press the last line ״ החזרה או החלפה של מוצר תקול״ 4.enter ״כבר עברו 14 יום ממועד הרכישה״ | 1.The customer service page will open 2.We will reach 4 lines of customer service 3.A page for filling in details will open We fill Telephone / Serial |  | Pass
SERV-3-11 | 1.Enter the site״ksp״ 2.go to the ״מידע ופעולות״ 3. click on the first tab ״סניפים ושעות פעילות״ 4Enter the store in the search bar ״Ashdod״ | 1.Enters all branches of the company 2.And it seems that the branch does not have parking for the disabled |  | Fail
SERV-3-12
SERV-3-13
SERV-3-14
SERV-3-15
SERV-3-16
SERV-3-17
SERV-3-18
SERV-3-19
SERV-3-20
SERV-3-21
SERV-3-22
SERV-3-23
SERV-3-24
SERV-3-25
SERV-3-26
SERV-3-27
SERV-3-28
SERV-3-29
SERV-3-30
SERV-3-31
SERV-3-32
SERV-3-33
SERV-3-34
SERV-3-35
SERV-3-36
SERV-3-37
SERV-3-38
SERV-3-39
SERV-3-40

## NeededDavid
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario |  | Total Passed | 1 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 1 |  |  |  | Fail
prerequest | Open Website Successfully | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
Blocked
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link /bug | Comments
NED-3-01 | 1.enter "ksp" site go to We will go to the fifth row up to"דרושים" 2.We will fill in all the details Name, family, phone, email, ID, and we will add a file of Resume | The data was received in the system |  | Fail |  | They did not return an answer for 3 weeks
business 3-02 | 1.Enter "ksp" Click on the fourth option ״מחלקה עסקית״ 2.Click on the fourth line option ״פיתוח עסקי / מדיה ופרסום״ | We will receive three contact emails according to the subject of rentals, advertising, cooperation |  | Pass
NED-3-03
NED-3-04
NED-3-05
NED-3-06
NED-3-07
NED-3-08
NED-3-09
NED-3-10
NED-3-11
NED-3-12
NED-3-13
NED-3-14
NED-3-15
NED-3-16
NED-3-17
NED-3-18
NED-3-19
NED-3-20
NED-3-21
NED-3-22
NED-3-23
NED-3-24
NED-3-25
NED-3-26
NED-3-27
NED-3-28
NED-3-29
NED-3-30
NED-3-31
NED-3-32
NED-3-33
NED-3-34
NED-3-35
NED-3-36
NED-3-37
NED-3-38
NED-3-39
NED-3-40

## Bargains and surplus stockDavid
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario |  | Total Passed | 3 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 1 |  |  |  | Fail
prerequest | Open Website Successfully | Total N/A, N/R and Blocked | 1 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
Blocked
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link /bug | Comments
BARG-3-01 | 1.Login to the website to go to the third tab 2.click on ״מציאון ועודפי מלאי״ 3.Choose one product and click on the cart to continue purchasing 4.A window will open on the left side of the cart to continue browsing the site or go to the checkout to make a purchase | 1.We have reached the checkout and you can make a purchase of the selected product 2.At the time of purchase there is an option of collection from Eilat, and redemption of a coupon |  | Pass
BARG-3-02 | 1.Log on to the site go to "מציאון ועודפי מלאי" and choose 2-3 products and put them in the cart and click on continue to purchase | The cart page opens and a purchase option |  | Pass
BARG-3-03 | 1.entered the page ״מוצרי מציאון ועודפי מלאי״ 2.Click on "All Products״ 3.and put in the line for filtering an amount lower than the lowest amount there | Does not allow filtering and presents the product at the lowest amount listed on the website |  | Not Applicable
BARG-3-04 | 1.entered the page ״מוצרי מציאון ועודפי מלאי״ 2.Click on "All Products״ 3.Click on the filter line and select a product in the "gaming" category A type of gaming headset was chosen there ״HyperX Cloud Stinger 2״ 4.We will add to the cart and continue to make the purchase | 1.The purchase page has opened successfully |  | Pass
BARG-3-05 | 1.entered the site 2. go to "מציאון ועודפים" 3. Choose two products in a row from the same category | 1.The page opens and shows all the products. 2.We will get an error |  | Fail
BARG-3-06
BARG-3-07
BARG-3-08
BARG-3-09
BARG-3-10
BARG-3-11
BARG-3-12
BARG-3-13
BARG-3-14
BARG-3-15
BARG-3-16
BARG-3-17
BARG-3-18
BARG-3-19
BARG-3-20
BARG-3-21
BARG-3-22
BARG-3-23
BARG-3-24
BARG-3-25
BARG-3-26
BARG-3-27
BARG-3-28
BARG-3-29
BARG-3-30
BARG-3-31
BARG-3-32
BARG-3-33
BARG-3-34
BARG-3-35
BARG-3-36
BARG-3-37
BARG-3-38
BARG-3-39
BARG-3-40

## CartTanya
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario | Cart | Total Passed | 37 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 4 |  |  |  | Fail
precondition | Open Website Successfully | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
| Connecting to the system through an account | [5 empty] | Blocked
The site is open on the shopping cart page
3 products have been added to the shopping cart מק"ט: 268701; מק"ט: 57972 M289297:מק"ט
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
ACCE-2-1 | Open the site on the shopping cart page | The cart view page is displayed as it should be. In the desired color scheme and displays the design chosen for the corporate style of the company. |  | Pass
ACCE-2-2 | Scroll the page down of the page to view the display of out-of-stock products. | The product is displayed with the message "מוצרים שנוספו לעגלה ואינם זמינים במלאי" | Select product (מק"ט: M289297 ) | Pass
ACCE-2-3 | Scroll the page down of the page to view the display of out-of-stock products and click the button "עדכון חזרה למלאי" | A message window pops up: לידיעתך" "בקשתך התקבלה בהצלחה! אנו נודיע לך ברגע שהמוצר יחזור למלאי" | Select product (מק"ט: M289297 ) | Pass
ACCE-2-4 | Click on the product photo | The product description page is displayed |  | Pass
ACCE-2-5 | Click on the product name | The product description page is displayed |  | Pass
ACCE-2-6 | Click on the "מוצרים משלמים" button | Opens a scroll-list of possible additional products that are suitable for the product of this model | Select product (מק"ט: 268701 ) | Pass
ACCE-2-7 | Click on the "מוצרים משלמים" button and select one of the additional products using the button cart under product. | The cart page view with the added item in the product list is displayed | Select product (מק"ט: 268701 ) | Pass
ACCE-2-8 | Click on the "מוצרים משלמים" button and click on the product name | The product description page is displayed in a separate window | Select product (מק"ט: 268701 ) | Pass
ACCE-2-9 | Click to the button "כמות" "+" or "-" to change the order quantity | The number of order units is changed by pressing "+" or "-" next to the button "כמות" the number in top left to the shopping cart button will also change. The total amount of the shopping cart also changes | Select product (מק"ט: 268701 ) | Pass
ACCE-2-10 | Click to the button "כמות" "+" to change the order product quantity to 5 (מק"ט: 268701 ) | .It won't let you select a number more than 5 :The message appears in red "שימו לב לא ניתן להזמין יותר מ- 5 פריטים ממוצר זה" | Select product (מק"ט: 268701 ) | Pass
ACCE-2-11 | Click to the button "כמות" "+" to change the order product quantity to more than 5 (מק"ט: 268701 ) | The number of order units is changed to 5 the number in top left to the shopping cart button will also change | Select product (מק"ט: 268701 ) | Pass
ACCE-2-12 | Click to the button "כמות" "+" or "-" to change the order quantity | The number of order units is changed by pressing "+" or "-" next to the button "כמות" the number in top left to the shopping cart button will also change | Select product (מק"ט: 57972 ) | Pass
ACCE-2-13 | Click to the button "כמות" "+" to change the order product quantity to 5 (מק"ט: 57972) | The number of order units is changed to 5 the number in top left to the shopping cart button will also change "שימו לב לא ניתן להזמין יותר מ- 3 פריטים ממוצר זה." | Select product (מק"ט: 57972 ) | Fail |  | The number of units of the order does not change up to 5 quantityin In this category limit up to 3 units of product
ACCE-2-14 | Click on the "X" button on the left side of the product descriptio. | This product has been removed and not displayed in the cart | Select product (מק"ט: 293479) | Pass
ACCE-2-15 | Click on the "איפוס העגלה" button on the left side. | :A warning window pops up שימו לב האם אתם בטוחים שברצונכם לרוקן את הגלת הקניות? |  | Pass
ACCE-2-16 | Click on the "איפוס העגלה" button on the left side. Select button "סגור" | On the cart page do not change, all products are displayed in it |  | Pass
ACCE-2-17 | Click on the "איפוס העגלה" button on the left side. Select button "אישור" | The cart page is empty and nothing is displayed in it. |  | Pass
ACCE-2-18 | Click on the "איפוס העגלה" button on the left side. Select button "אישור" | The product number near the cart sign in the upper left corner has changed to 0 |  | Fail |  | The product number near the cart sign in the upper left corner not changed, only after refresh of the page.
ACCE-2-19 | Scroll the page down, and a benefit option for items in the shopping cart appears below the list of items שימו לב, הטבה לפניכם - אנא בחרו באפשרות הרצויה | You can choose options to purchase headphones with a discount, receive a free charger or complete a purchase without any benefits |  | Pass
ACCE-2-20 | Scroll page down and select product with price 0: מטען קיר Apple 20W USB-C מק"ט: 114917 | The number of order units is changed , the number in top left to the shopping cart button will also change. The total amount of the shopping cart the same And additional line is displayed "הטבה מיוחדת" |  | Pass
ACCE-2-21 | :Scroll the page down and select a offer חבילת מסטיקים -2 חבילות ב- 10 ש"ח לחבילה -3 חבילות ומעלה ב8 ש"ח לחבילה! Click button לחץ לבחירה And select 3 products with button בחר | The cart page view with the added item in the product list is displayed. The number of product units is changed, and the number in the top left of the shopping cart button will also change. The total amount of the shopping carts change the amount varies according to the terms of the advertisement an additional line is displayed "הטבה מיוחדת" |  | Pass
ACCE-2-22 | :Scroll the page down and select a offer חבילת מסטיקים -2 חבילות ב- 10 ש"ח לחבילה -3 חבילות ומעלה ב8 ש"ח לחבילה! Click button לחץ לבחירה And select 1 products with button בחר | The cart page view with the added item in the product list is displayed. The number of product units is changed, and the number in the top left of the shopping cart button will also change. The total amount of the shopping carts change the amount varies according to the terms of the advertisement an additional line is displayed "הטבה מיוחדת" |  | Fail |  | The discount works even when conditions are not met
ACCE-2-23 | Scroll the page down and select a offer: 6 שקיות רב פעמיות לקניות HomeSet מק"ט: 292609 Click button הוסף לסל | The cart page view with the added item in the product list is displayed. The number of product units is changed, and the number in the top left of the shopping cart button will also change. The total amount of the shopping carts change the amount varies according to the terms of the advertisement an additional line is displayed "הטבה מיוחדת" |  | Pass
ACCE-2-24 | Scroll the page down and select איסוף באילת A pop-up window opens with a list of the addresses of the KSP offices Select one of the addresses of the KSP offices | Select the address of the office KSP in Eilat to pick up the order |  | Pass
ACCE-2-25 | Scroll the page down and select המשיכו ברכישה | The checkout page opens |  | Pass
ACCE-2-26 | Scroll the page down and select מימוש קופון Enter coupon number and phone number and click : מימוש הקופון | The total amount is changed of the cart including coupon discount on the cart page displayed the message הזנתם קוד קופון "חגיגת קופונים בטלגרם" המקנה הנחה מיידית ברכישה ממגון המוצרים המשתתפים במבצע אין כפל קופונים - במידה וברצונכם להשתמש בקופון אחר יש ללחוץ על הסרת קופון. הסרת הקופון | CM102296N4K coupon number 054-73416** telefon number | Pass
ACCE-2-27 | Click on the product photo | The product description page is displayed | Not connected to the system account | Pass
ACCE-2-28 | Click on the product name | The product description page is displayed | Not connected to the system account | Pass
ACCE-2-29 | Click on the "מוצרים משלמים" button | Opens a scroll-list of possible additional products that are suitable for the product of this model | Not connected to the system account Select product (מק"ט: 268701 ) | Pass
ACCE-2-30 | Click on the "מוצרים משלמים" button and select one of the additional products using the button cart under product. | The cart page view with the added item in the product list is displayed | Not connected to the system account Select product (מק"ט: 268701 ) | Pass
ACCE-2-31 | Click on the "מוצרים משלמים" button and click on the product name | The product description page is displayed in a separate window | Not connected to the system account Select product (מק"ט: 268701 ) | Pass
ACCE-2-32 | Click to the button "כמות" "+" or "-" to change the order quantity | The number of order units changed pressing "+" or "-" next to the button "כמות" the number in top left to the shopping cart button changed. The total amount of the shopping cart changed. | Not connected to the system account Select product (מק"ט: 268701 ) | Pass
ACCE-2-33 | Click to the button "כמות" "+" to change the order product quantity to 5 (מק"ט: 268701 ) | Does not select a number greater than 5 :The message in red "שימו לב לא ניתן להזמין יותר מ- 5 פריטים ממוצר זה." | Not connected to the system account Select product (מק"ט: 268701 ) | Pass
ACCE-2-34 | Click to the button "כמות" "+" to change the order product quantity to more than 5 (מק"ט: 268701 ) | The number of order units changed to 5 the number in top left to the shopping cart button changed. | Not connected to the system account Select product (מק"ט: 268701 ) | Pass
ACCE-2-35 | Click to the button "כמות" "+" or "-" to change the order quantity | The number of order units changed greater "+" or less "-" next to the button "כמות" the number in top left to the shopping cart button changed. | Not connected to the system account Select product (מק"ט: 57972 ) | Pass
ACCE-2-36 | Click to the button "כמות" "+" to change the order product quantity to 5 (מק"ט: 57972) | The number of order units changed to 5 the number in top left to the shopping cart button changed. "שימו לב לא ניתן להזמין יותר מ- 3 פריטים ממוצר זה." | Not connected to the system account Select product (מק"ט: 57972 ) | Pass
ACCE-2-37 | Click on the "X" button on the left side of the product descriptio. | This product has been removed and not displayed in the cart | Not connected to the system account Select product (מק"ט: 293479) | Pass
ACCE-2-38 | Click on the "איפוס העגלה" button on the left side. | :A warning window pops up שימו לב האם אתם בטוחים שברצונכם לרוקן את הגלת הקניות? | Not connected to the system account | Pass
ACCE-2-39 | Click on the "איפוס העגלה" button on the left side. Select button "סגור" | On the cart page do not change, all products are displayed in it | Not connected to the system account | Pass
ACCE-2-40 | Click on the "איפוס העגלה" button on the left side. Select button "אישור" | The cart page is empty and nothing is displayed in it. | Not connected to the system account | Pass
ACCE-2-41 | Scroll the page down, and a benefit option for items in the shopping cart appears below the list of items שימו לב, הטבה לפניכם - אנא בחרו באפשרות הרצויה Chose one of the options | Choose options to purchase receive a free charger, or complete a purchase without any benefits | Not connected to the system account | Fail |  | You can't choose options to purchase receive a free charger, or complete a purchase without any benefits because you are not in the system.
ACCE-2-42

## OrderTanya
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario | Cart | Total Passed | 23 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 1 |  |  |  | Fail
Prerequisite | Open Website Successfully | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
Precondition | Connecting to the system through an account | [5 empty] | Blocked
The site is open on the order page
2 products have been added to shopping cart M289297 :מק"ט מק"ט: 215373
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
ORDER-5-1 | Click the button נמשיכו ברכישה | You enter from the shopping cart page by clicking the button נמשיכו ברכישה |  | Pass
ORDER-5-2 | Click the button עריכת פרטים and update first name and last name in Hebrew and click button שמירה | Your personal details are updated in Hebrew for an order פרטים אישיים המעודכנים עבור הזמנתך | First name: טטיאנה Last name: זימה | Pass
ORDER-5-3 | Click the button עריכת פרטים and update the first name and last name in English and click button שמירה | Your personal details are updated in English for an order פרטים אישיים המעודכנים עבור הזמנתך | First name: Tatyana Last name: Zima | Pass
ORDER-5-4 | Click the button עריכת פרטים and update new adressin Hebrew and click button שמירה | Your new address has been updated | City: ראשון לציון Street: שינקין House:14 Apartment:25 | Pass
ORDER-5-5 | Click the button עריכת פרטים and update new adress in English and click enter. | You cannot update the new address in English. A message is displayed ארעה שגיאה | City: Rishon lezion Street: Shenkin House:14 Apartment:25 | Pass
ORDER-5-6 | Click the button הצגת כתובות נוספות | Additional address is shown |  | Pass
ORDER-5-7 | Click the button הסתרת כתובות נוספות | Additional address is hidden |  | Pass
ORDER-5-8 | Click the button הצגת כתובות נוספות and double click on the additional address. | You can switch between the addresses |  | Pass
ORDER-5-9 | Click the button שינוי שיטת משלוח and check off איסוף בסניף KSP in the windows that open, write the city and choose from a list of affiliates and click button המשך | Under the window with the name of the branch, opened a map of the branch location with the exact address and opening hours. |  | Pass
ORDER-5-10 | Click the button שינוי שיטת משלוח and move the cursor to the green box with the message: חינם ויגיע מהר יותר | A message appears above the field: במרבית המקרים איסוף מהסניף יחסוך 1-2 ימים |  | Pass
ORDER-5-11 | Click the button שינוי שיטת משלוח and move the cursor to the question mark ? near to איסוף בססניף KSP | A message appears above the mark: *ימים - מתייחס לימי עסקים החל מרגע אישור העסקה בחברת האשראי *מספר ימי משלוח למרבית נקודות האיסוף (ראו פירוט בעגלת הקניות) |  | Pass
ORDER-5-12 | Click the button שינוי שיטת משלוח and check off משלוח למגוון נקודות איסוף in the windows that open, choose the city and street and click button המשך | A list of collection points will open to select the appropriate one. The total price will change to include shipping costs | City : ראשון לציון Street : שינקין | Pass
ORDER-5-13 | Click the button שינוי שיטת משלוח and move the cursor to the question mark ? near to משלוח למגוון נקודות איסוף | A message appears above the mark: *ימים - מתייחס לימי עסקים החל מרגע אישור העסקה בחברת האשראי *לוקר/חנות -חנויות ורשתות מובחרות בפריסה ארצית, בחלק מהמקרים מוגבל לפריט יחיד בעגלת הקניות (ראו פירוט בעגלת הקניות |  | Pass
ORDER-5-14 | Click the button שינוי שיטת משלוח and check off משלוח לבית הלקוח | Under the window with details of the order, you see message: הזמנתך תסופק ב- 1 חבילות סה"כ חבילות שנדרשות למשלוח כלל הפריטים (חינם ובתשלום) - 1 סה"כ חבילות זכאיות למשלוח חינם - 0 חבילות בתשלום (1) x מחיר חבילה בודדת (₪28) סה"כ עלות משלוח: ₪28 משלוח לבית הלקוח בכתובת שינקין 4, ראשון לציון The total price will change to include shipping costs |  | Pass
ORDER-5-15 | Click the button שינוי שיטת משלוח and move the cursor to the question mark ? near to משלוח לבית הלקוח | A message appears above the mark: *ימים - מתייחס לימי עסקים החל מרגע אישור העסקה בחברת האשראי *למעט ישובים מרוחקים |  | Pass
ORDER-5-16 | Click the button שינוי שיטת משלוח and check off משלוח מהיר | Error message pops up שגיאה! משלוח מהיר אינו זמין עבור הפריטים שבחרת לרכוש |  | Fail
ORDER-5-17 | Click the button שינוי שיטת משלוח and move the cursor to the question mark ? near to משלוח לבית הלקוח | A message appears above the mark: *הזמנות שיתקבלו עד שעה 11:00 בבוקר תתאפשר מסירה עוד באותו היום *הזמנות שיתקבלו לאחר שעה 11:00 בבוקר תתאפשר מסירה ביום למחרת *לתשומת לבך! - משלוח מהיר מתבצע ישירות מסניף סמוך ולכן יוצע כאפשרות בעגלת הקניות רק באם הפריטים בהזמתך נמצאים כולם יחדיו במלאי אחד הסניפים הסמוכים לכתובת המשלוח |  | Pass
ORDER-5-18 | Click the button שינוי שיטת משלוח and check off איסוף באילת (הזמנת שריון) A pop-up window opens with a list of the addresses of the KSP offices Select one of the addresses of the KSP offices | You will be redirected to a page עגלת קניות אילת (ללא מע"מ) The total price will change less tax |  | Pass
ORDER-5-19 | Click the button שינוי שיטת משלוח and move the cursor to the question mark ? near to איסוף באילת (הזמנת שריון ) | A message appears above the mark: מתכננים ביקור באאפשרותכםילת? באפשרותכם להזמין את המוצרים לפני הגיתכם לאילת ומוצרים ימתינו עבורכם בסניף. פשוט בחרו את המוצרים שברצונכם לרכוש באילת ובחרו באפשרות "איסוף באילת" בעגלת הקניות וציינו סניף האיסוף. בעת סיום ההזמנה תתבקשו למלא פראי כרטיס אשראי כאמצי ביטחון בלבד. בקשה להזמנה באילת *בהתאם למלאי יזמין בסניפים התומכים בשירות |  | Pass
ORDER-5-20 | Click the button שינוי שיטת משלוח and check off משלוח באילת - חדש! A pop-up window opens with a list of the addresses of the KSP offices Select one of the addresses of the KSP offices | You will be redirected to the שירות הזמממנה מוקדמת page, where you must enter the address and date of delivery. You must mark all the conditions under which the order transfer is possible. The total price will change minus taxes, but the cost of transportation will be added |  | Pass
ORDER-5-21 | Click the button שינוי שיטת משלוח and move the cursor to the question mark ? near to איסוף באילת (הזמנת שריון ) | A message appears above the mark: משלוח באילת בנוכחות בעל הכרטיס ובהצגת תעודה מזהה * האפשרות למשלוח באילת מותנית בזמינות המלאי ותנאי אספקה אפשרות זו תוצג בעגלת הקניות. |  | Pass
ORDER-5-22 | Scroll through the list of shipping methods and check the box next to the item אני מאשר/ת עדכונים ומבצעים באמצעות מסרון SMS * בהתאם לבקשתכם בעבר, חשבונית העסקה תשלח בדוא "ל במקום חשבונית מנייר (כולל פתק החלפה) | You can check or uncheck אני מאשר/ת עדכונים ומבצעים באמצעות מסרון SMS * בהתאם לבקשתכם בעבר, חשבונית העסקה תשלח בדוא "ל במקום חשבונית מנייר (כולל פתק החלפה) |  | Pass
ORDER-5-23 | Scroll down the page to the order total סיכום הזמנה click to the button הצגת פירוט | Opens the list of products כמות,מחיר יח', מחיר,מק"ט,תאור מוצר,סכום ביניים, עלויות שילוח,סה"כ |  | Pass
ORDER-5-24 | Scroll down the page and click to the button המשך ומעבר לתשלום | You will be redirected to the payment page available for 9 minutes with a countdown clock. |  | Pass

## Buying guidesTanya
Test Info |  | Test Summary |  |  |  |  | Not Started
Test Scenario | Cart | Total Passed | 6 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 0 |  |  |  | Fail
Prerequisite | Open Website Successfully | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
Precondition | Connecting to the system through an account | [5 empty] | Blocked
The site is open on the buying guides page
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
GUIDE-5-01 | Click to the מוצרי חשמל | You will be redirected to a page with a list of buying guides for a variety of electronic home goods |  | Pass
GUIDE-5-02 | Click to the מוצרי חשמל and after that click to the מה עלינו לחפש במדיח כלים? המדריך המלא לרכישת מדיח הכלים האידיאלי עבורי | You will be redirected to the page with a guide on how to choose a dishwasher and important information pertaining to the subject |  | Pass
GUIDE-5-03 | Click to the צילום | You will be redirected to the camera buying guide page with a guide המצלמות הטובות ביותר למתחילים |  | Pass
GUIDE-5-04 | Click to the צילום and after that click on the חזרה לעולם הצילום | You will be redirected to the page with camera and camera accessories |  | Pass
GUIDE-5-05 | Click to the בישול | You will be redirected to the guide page המדריך לבישול ואפייה ביתיים |  | Pass
GUIDE-5-06 | Click to the בישול and after that click to the המדריך לבישול ואפייה ביתיים | You will be redirected to the page with a product list and information about this product which can be purchased on the website |  | Pass
GUIDE-5-07
GUIDE-5-08
GUIDE-5-09
GUIDE-5-10
GUIDE-5-11
GUIDE-5-12
GUIDE-5-13
GUIDE-5-14
GUIDE-5-15
GUIDE-5-16
GUIDE-5-17
GUIDE-5-18
GUIDE-5-19
GUIDE-5-20

## Search Hadas LEFT THE PROJECT
Test Info | Search | Test Summary |  |  |  |  | Not Started
Test Scenario | Search | Total Passed | 0 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 0 |  |  |  | Fail
| Open Website Successfully | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
| Connecting to the system to through an account | [5 empty] | Blocked
The site is open on the home page
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
SEAR-4-1
SEAR-4-2
SEAR-4-3
SEAR-4-4
SEAR-4-5
SEAR-4-6
SEAR-4-7
SEAR-4-8
SEAR-4-9
SEAR-4-10
SEAR-4-11
SEAR-4-12
SEAR-4-13
SEAR-4-14
SEAR-4-15
SEAR-4-16
SEAR-4-17
SEAR-4-18
SEAR-4-19
SEAR-4-20
SEAR-4-21
SEAR-4-22
SEAR-4-23
SEAR-4-24
SEAR-4-25
SEAR-4-26
SEAR-4-27
SEAR-4-28
SEAR-4-29
SEAR-4-30
SEAR-4-31
SEAR-4-32
SEAR-4-33
SEAR-4-34
SEAR-4-35
SEAR-4-36
SEAR-4-37
SEAR-4-38
SEAR-4-39
SEAR-4-40

## Gift card Hadas LEFT THE PROJEC
Test Info | Search | Test Summary |  |  |  |  | Not Started
Test Scenario | Search | Total Passed | 0 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 0 |  |  |  | Fail
| Open Website Successfully | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
| Connecting to the system to through an account | [5 empty] | Blocked
The site is open on the home page
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
GIFT-4-01
GIFT-4-02
GIFT-4-03
GIFT-4-04
GIFT-4-05
GIFT-4-06
GIFT-4-07
GIFT-4-08
GIFT-4-09
GIFT-4-10
GIFT-4-11
GIFT-4-12
GIFT-4-13
GIFT-4-14
GIFT-4-15
GIFT-4-16
GIFT-4-17
GIFT-4-18
GIFT-4-19
GIFT-4-20
GIFT-4-21
GIFT-4-22
GIFT-4-23
GIFT-4-24
GIFT-4-25
GIFT-4-26
GIFT-4-27
GIFT-4-28
GIFT-4-29
GIFT-4-30
GIFT-4-31
GIFT-4-32
GIFT-4-33
GIFT-4-34
GIFT-4-35
GIFT-4-36
GIFT-4-37
GIFT-4-38
GIFT-4-39
GIFT-4-40

## Trade-In Hadas LEFT THE PROJECT
Test Info | Search | Test Summary |  |  |  |  | Not Started
Test Scenario | Search | Total Passed | 0 |  |  |  | Pass
Test Environment | QA environment | Total Failed | 0 |  |  |  | Fail
| Open Website Successfully | Total N/A, N/R and Blocked | 0 |  |  |  | Not Applicable
Test Data Source | https://ksp.co.il/web/ | Total Remaining | 0 |  |  |  | Not Relevant
| Connecting to the system to through an account | [5 empty] | Blocked
The site is open on the home page
Test Case ID | Test Case Description | Expected Result | Test Data | Status | Defect Link | Comments
GIFT-4-01
GIFT-4-02
GIFT-4-03
GIFT-4-04
GIFT-4-05
GIFT-4-06
GIFT-4-07
GIFT-4-08
GIFT-4-09
GIFT-4-10
GIFT-4-11
GIFT-4-12
GIFT-4-13
GIFT-4-14
GIFT-4-15
GIFT-4-16
GIFT-4-17
GIFT-4-18
GIFT-4-19
GIFT-4-20
GIFT-4-21
GIFT-4-22
GIFT-4-23
GIFT-4-24
GIFT-4-25
GIFT-4-26
GIFT-4-27
GIFT-4-28
GIFT-4-29
GIFT-4-30
GIFT-4-31
GIFT-4-32
GIFT-4-33
GIFT-4-34
GIFT-4-35
GIFT-4-36
GIFT-4-37
GIFT-4-38
GIFT-4-39
GIFT-4-40